VOLUME 2

SECTION 3SPECIAL CONDITIONS FOR EUROPEAN UNION EXTERNAL ACTIONS

# CONTENTS

# These conditions amplify and supplement the general conditions governing the contract. Unless the special conditions provide otherwise, the general conditions remain fully applicable. The numbering of the articles of the special conditions is not consecutive but follows the numbering of the general conditions. Exceptionally, and with the approval of the competent European Commission departments, other clauses can be indicated to cover particular situations.

# Contract value

# The contracting authority hereby agrees to pay to the contractor, in consideration of the execution and completion of the works and remedying of defects therein, the amount of the contract value mentioned in article 2 of the Main Conditions or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the contract. VAT will be paid in compliance with the binding regulations, national law and international agreements concerning the execution of the project.

# The amount of the contract value mentioned in article 2 of the Main Conditions shall be composed of:

- Contract price (excluding VAT/other taxes) EUR <amount>

The EU component EUR<amount>

[where necessary, <enter other sources of financing>]

-	VAT and other taxes EUR <amount>  	Only in case VAT/taxes are to be paid by the contracting authority to the contractor, fill in the amount thereof. The contract price excluding VAT/other taxes, must coincide with the total of Volume 4.2.2 (total lump-sum price).

# Order of precedence of contract documents

The following documents shall be deemed to form and be read and construed as part of this contract, in the following order of precedence:

- The main conditions

- the special conditions,

- the general conditions,

- the bill of quantities (after arithmetical corrections) and detailed breakdown of prices.

- the technical and/or performance specifications,

- the design documentation (drawings),

- any other documents forming part of the contract.

The various documents making up the contract shall be deemed to be mutually explanatory; in cases of ambiguity or divergence, they shall prevail in the order in which they appear above. Addenda shall have the order of precedence of the document they are amending.

Article 2	Language of the contract

2.1	The language used shall be English.

Article 4	Communication

4.1	Communication details

4.4	Communication via electronic exchange system (EES)

An electronic system will be used by the contracting authority and the contractor for all stages of implementation including, inter alia, management of the contract (amendments and administrative orders), reporting (including reporting on results) and payments. The contractor will be required to register in and use the appropriate electronic exchange system to allow for the e-management of the contract.

4.5 & 4.6 	Mail or email communication

If communications through the Portal have not been activated or a certain type of communication is not yet supported by the Portal, communications will be sent via email, or, exceptionally, on paper, via mail services, to the following addresses, until communications via the Portal are activated.

For the purpose of this contract, mail or email communications must be sent to the following addresses:

Contracting authority:

Municipality of Uzunkopru

Full official address: Cumhuriyet Mah. 19 Mayıs Cad. No 160, 22200 Uzunkopru, Edirne, Türkiye

Email: yaziisleri@uzunkopru.bel.tr

Contractor (or leader in the case of a joint tender):

[Full name]

[Function]

[Company name]

[Full official address]

Email: [complete]

Article 5	Supervisor and supervisor’s representative

5.2	The Contracting Authority shall appoint the Supervisor for the implementation of the works. The Supervisor shall be appointed by Uzunköprü Municipality and shall perform the supervision and control of the works on behalf of the Contracting Authority in accordance with the Contract, the approved designs, technical specifications and applicable legislation. The Supervisor shall have access to the site and to all documents, records, materials and information necessary for the proper performance of his/her duties.

5.3	The Supervisor shall be responsible for supervising and controlling the execution of the works on behalf of the Contracting Authority, including checking the compliance of the works with the Contract, approved projects, technical specifications, applicable standards and relevant legislation. The Supervisor may issue instructions and administrative orders within the powers granted under the Contract. The Supervisor may delegate, in writing, specific duties and authority to a Supervisor’s Representative in accordance with Article 5 of the General Conditions.

The Contractor shall comply with the lawful instructions of the Supervisor issued within the scope of the Contract. Neither the Supervisor nor the Supervisor’s Representative shall have authority to relieve the Contractor of its contractual obligations or to authorise variations, extensions of time or additional costs except as expressly provided for under the Contract and applicable procedures.

5.4	Administrative orders shall be issued in writing by the Supervisor, dated and consecutively numbered, and shall be recorded in the administrative orders register. Copies of administrative orders shall be delivered to the Contractor’s Representative against acknowledgement of receipt. The supervision and control of the works shall be carried out by the control/supervision team appointed by Uzunköprü Municipality. Inspection, testing, measurement, verification and other control activities shall be performed in accordance with the Contract and applicable legislation. The acceptance of the completed works shall be carried out by a separate acceptance commission duly appointed by the Contracting Authority, in accordance with the applicable rules and procedures.

Article 9	Access to the site

9.1	The contractor is reminded that there is a head of delegation of the European Unionin the state of the contracting authority. The contractor is obliged to give the head of delegation free access to its sites, factories, workshops, etc., and generally assist the head of delegation, like the project Supervisor, in the performance of his duties. The same provisions also apply to the appointed representatives of the head of delegation.

All correspondence between the contractor and the contracting authority or project supervisor must be copied, for information, to the head of delegation of the European Commission at the following official address:

Managing Authority

Ministry of Regional Development and Public Works

Territorial Cooperation Management Directorate 
Sofia 1000, Bulgaria 
9 Stefan Karadzha Str.

National Authority (NA)

Ministry of Foreign Affairs

Directorate for EU Affairs

Mustafa Kemal Mahallesi 2082.

Cadde No: 5 Çankaya/Ankara, Türkiye

Joint Secretariat - main office in Haskovo, BG

2, Patriarh Evtimiy str. 
 Offices 88, 89, 90, 91 
 6300 Haskovo, Bulgaria

Joint Secretariat – branch office in Edirne, TR

Sabuni Mah. Saraçlar Cad. Eser Yavaş İş Merkezi,

Kat:3, No:3-4 Edirne/ Merkez

Article 12	General obligations

12.9	Contractor shall ensure the highest visibility to the financial contribution of the European Union and Interreg IPA Bulgaria–Türkiye Cross-Border Cooperation Programme 2021-2027 through placing an info board on the work area. The info board shall be prepared and placed at the construction site according the visibility requirements and guidelines provided in the Communication and Visibility Manual for EU External Actions, and the Communication and Visibility Guidelines of the Interreg IPA Bulgaria–Türkiye Cross-Border Cooperation Programme 2021-2027.

Article 15	Performance guarantee

15.1	The amount of the performance guarantee will be 6% of the amount of the contract and any addenda thereto.

15.8.    The performance guarantee shall be released within 60 days of the issuing of signed final acceptance after one year of the provisional acceptance and statement of account, except for amounts which are the subject of amicable settlement, conciliation, arbitration or litigation

Article 16	Liabilities and insurance

16.1 a)	By way of derogation from Article 16.1, a) paragraph 2, of the general conditions, compensation for damage to the works resulting from the contractor's liability in respect of the contracting authority is capped at an amount equal to the contract value.

16.1 b)	By way of derogation from Article 16.1, b), paragraph 2, of the general conditions, compensation for damage resulting from the contractor's liability in respect of the contracting authority is capped at an amount equal to the contract value.

Article 17	Programme of implementation of tasks

17.1	The contractor shall provide the supervisor with a simplified programme of implementation of the tasks. This programme shall include at least the order and time limits in which the contractor proposes to carry out the works, and shall be based on the tranches foreseen in Article 49.1 of the special conditions.

17.2. 	The supervisor shall return this document to the contractor with any relevant remarks within 10 days of receipt, save where the supervisor, within those 10 days, notifies the contractor of its wish for a meeting in order to discuss the documents submitted.

Article 19	Contractor’s drawings and execution studies

19.1	In addition to the requirements set out in the General Conditions, the Contractor shall, at its own expense, prepare and submit to the Supervisor for approval the detailed execution drawings, shop drawings, method statements, samples and technical details necessary for the proper execution of the Works, only insofar as such documents are not already provided in the approved Restoration Project.

The Contractor shall carry out the Works on the basis of the Restoration Project approved by the Edirne Regional Council for the Conservation of Cultural Heritage by Decision No. 5662 dated 28.01.2019, together with the other Contract Documents. Any drawings, details, samples, method statements or other technical documents to be prepared by the Contractor under this Article shall be limited to the detailed execution of the approved Restoration Project and shall not constitute a new design or alter the approved restoration decisions.

The Contractor shall not make any alteration, omission, addition or deviation from the approved Restoration Project without the prior written instruction of the Contracting Authority and, where required by applicable legislation, the prior approval of the Edirne Regional Council for the Conservation of Cultural Heritage.

19.7	The operation and maintenance manuals, where applicable, as well as the as-built drawings and other technical documentation to be submitted by the Contractor before provisional acceptance shall be prepared in Turkish.

Article 20	Sufficiency of tender prices

20.1. 	In addition to the provisions of the General Conditions, the Contractor shall be deemed, prior to the submission of its tender, to have inspected and examined the existing cultural heritage building, its surroundings and all areas relevant to the execution of the Works, and to have satisfied itself as to the existing physical condition of the building, the accessibility of the site, the conditions for carrying out restoration works, the existing building elements and materials, and all other circumstances which may reasonably influence the execution of the Works and the preparation of its tender.

The Contractor shall be deemed to have taken into account, in the preparation of its tender prices, the specific requirements applicable to the restoration and conservation of the protected cultural heritage property, including the careful dismantling, protection, storage, repair, conservation and reinstatement of existing building elements and materials, where required by the approved project documentation and the applicable legislation.

The Contractor shall also be deemed to have examined the approved restoration project, technical specifications, bills of quantities, available surveys and other tender documents and to have obtained all information reasonably necessary for the proper pricing and execution of the Works.

20.2. 	The tender prices shall be deemed to include all labour, materials, equipment, temporary works, transport, handling, protection, storage, scaffolding, access arrangements, site organisation and other costs necessary for the proper and complete execution of the Works in accordance with the Contract, unless expressly provided otherwise in the Contract.

20.3. 	The provisions of Article 20 of the General Conditions shall apply without prejudice to the provisions of the Contract concerning variations, unforeseen circumstances, additional works, extensions of time and any other circumstances which, under the Contract, may entitle the Contractor to an adjustment of the Contract price or time for completion.

20.4. 	No additional payment shall be made for works, materials or activities which are reasonably foreseeable from the tender documents, the approved project documentation, the site inspection and the nature of the restoration works and which are necessary for the proper and complete execution of an item included in the Bill of Quantities or Price Schedule offered by the contractor.

Article 21	Exceptional risks

21.4	Exceptional risks may include physical conditions or artificial obstructions affecting the existing protected cultural heritage building which could not reasonably have been identified or foreseen by an experienced contractor on the basis of the tender documents, the approved restoration project, available surveys and information, and a reasonable inspection of the site before submission of the tender.

Such conditions may include, without limitation, previously concealed or inaccessible structural elements, unexpected conditions of foundations or load-bearing elements, concealed deterioration or structural damage, previously unidentified original building elements or materials, or other physical conditions which materially affect the execution of the restoration works and which could not reasonably have been foreseen at the time of tendering.

Where such conditions are encountered, the Contractor shall immediately protect the affected building elements and shall notify the Supervisor in writing the applicable notification requirements of the Contract. The Contractor shall not proceed with works that could damage, alter or remove potentially significant original or historic building elements without the written instructions of the Supervisor, except where immediate action is necessary to prevent imminent damage to persons or the building.

For the purposes of the Contract, normal seasonal weather conditions expected in the project area shall be deemed to have been taken into account by the Contractor in the preparation of its tender and work programme.

Potential exceptional weather conditions may include unusually severe and prolonged rainfall, snowfall, freezing conditions, storms, high winds, flooding or other extreme weather events of such severity that they materially prevent or substantially interfere with the safe execution of the Works.

Such weather conditions shall be assessed on the basis of their actual impact on the execution of the Works and the applicable safety requirements. In accordance with Article 21.4 of the General Conditions, weather conditions shall not entitle the Contractor to additional payment under Article 55.

Article 24	Interference with traffic

24.1	The Contractor shall not close, obstruct or otherwise impede public roads, streets, pavements or other communication links serving the Site without the prior written approval of the Contracting Authority and/or the competent authority.

Where the execution of the Works requires a temporary restriction, partial closure or diversion of pedestrian or vehicular traffic, the Contractor shall obtain all necessary permissions and shall implement the traffic arrangements required by the competent authorities. Any such restriction shall be limited to the minimum area and period necessary for the safe execution of the Works.

The Contractor shall ensure that access to adjacent properties, public facilities and emergency services is maintained at all times, unless otherwise authorised by the competent authority.

24.2	The Contractor shall take all necessary measures to ensure the safety and continuity of pedestrian and vehicular traffic in and around the Site. Such measures shall include, where applicable, the provision and maintenance of appropriate barriers, warning signs, lighting, pedestrian access routes and temporary traffic arrangements.

The Contractor shall organise the delivery and removal of construction materials, equipment and waste so as to minimise disruption to local traffic and public access. Heavy vehicles shall use only routes suitable for their weight and dimensions and shall comply with all applicable weight, height and other traffic restrictions.

The Contractor shall be responsible for any damage caused to roads, pavements, kerbs, public infrastructure or other communication links as a result of the transport of materials, plant or equipment required for the Works and shall, at its own expense, promptly repair such damage to the satisfaction of the competent authority and the Supervisor.

Any special measures required to protect roads, pavements, tracks or other communication links due to the Contractor's operations shall be at the Contractor's expense.

The Contractor shall inform the Supervisor in advance of any planned transport operation or activity which may materially affect traffic or public access and shall coordinate such activities with the Contracting Authority and the relevant competent authorities.

Article 27	Demolished materials

27.2	The natural ground shall not be excavated or disturbed unnecessarily.

- If excavation exceeds the dimensions specified in the project, the cost of the excess excavation will not be paid.

- The excavation base shall not be left exposed to natural conditions for extended periods. Rainwater or groundwater must be prevented from seeping into or accumulating on the excavation base.

- Excavation dimensions will be taken from the plankote and project plans. No classification will be given for the type of excavation. The casting location and transportation costs are included in the excavation price, and backfilling is included in the excavation price.

- The contractor shall take measures such as battering, shoring, or other stabilization methods to prevent slippage or collapse during excavation. Safety measures including guardrails, barrier tapes, and warning signs shall be provided to prevent falls or accidents at the edges of excavations.

- In all excavations, measures shall be taken to prevent damage to the soil, deformation of formwork and equipment, or muddiness caused by groundwater or rainwater entering and accumulating in the excavation area.

- If such risks exist, it is the contractor’s responsibility to have necessary equipment and tools (e.g., pumps, hoses, sand, crowbars, etc.) available on site.

- The cost of excavation disposal, any expenses arising in connection with the excavation, and any damages or losses related to the safety of the parcels surrounding the construction site shall be under the responsibility of the Contractor.

Article 29	Temporary works

29.2	The Contractor shall take into account the observations and instructions of the Supervisor and shall remain fully responsible for the design, stability, safety, adequacy and proper execution of the temporary works.

Article 30	Soil studies

30.1	NA

Article 32	Patents and licenses

32.1	The provisions of Article 32 shall apply in full to all patents, licences, drawings, designs, models, trademarks, copyrights and other intellectual, industrial or property rights used or developed in connection with the Works.

Article 34	Period of implementation of tasks

34.1	The period of implementation of tasks is 6 six months.

Within 10 (ten) days from the date of signing the Contract, the site shall be handed over and the works shall be commenced.

The Contractor shall complete the entire undertaking – construction works and make it ready for provisional acceptance within 180 (one hundred eighty) days from the date of site handover. As the calculation of the period already takes into account the time during which weather conditions make work technically unsuitable, as well as official holidays, no further extension of time shall be allowed for these reasons.

If the Contractor fails to be present for the site handover within the period specified in the contract, this situation shall be recorded at the end of the period by a committee, including the supervisor appointed by the Contracting Authority, and the period of the works shall be deemed to have commenced.

Article 36	Delays in the implementation of tasks

36.1	The rate of liquidated damages for delays in the completion of works shall be 0.1% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 10 % of the contract price or, if the contract is subdivided into phases, 10 % of the price of the phase concerned.

Article 39	Work register

39.1    The work register is required and will be accomplished according to Art. 39 in General Conditions and as per Turkish legislation.

39.2	The statements shall be prepared according to the rules in internal legislation, namely to the general conditions of the investment works related to the open area works. All statements shall be signed by the Contractor and Supervisor (CA’s experts).

Article 40	Origin and quality of works and materials

40.1	All goods purchased and materials under the contract may originate in any country.

When importing goods, any change in the specified origin must be pointed out to the project supervisor and approved by him.

40.2	The works and the objects, appliances, equipment or materials used in their construction must comply with:

(a) 	the approved restoration and conservation project and all drawings, technical specifications, details, surveys, schedules and other technical documents forming part of the Contract;

(b) 	the requirements and conditions set out in the Bill of Quantities and the Technical Specifications;

(c) 	the applicable decisions, approvals and requirements of the competent authorities responsible for the protection and conservation of the cultural heritage property;

(d) 	the applicable national technical standards and legislation, and, where specified in the Contract, the relevant European or international standards.

For restoration and conservation works, materials and products shall be compatible with the existing building and shall be selected and applied in accordance with the approved restoration project and the requirements of the competent cultural heritage authorities.

Where samples, patterns or mock-ups are specified in the Contract or requested by the Supervisor, the Contractor shall submit them to the Supervisor for approval before the relevant materials or works are incorporated into the Works.

The approved drawings, specifications, samples, patterns and other reference documents shall be kept available at the Site or at another location agreed with the Supervisor for the purpose of identification and verification throughout the period of implementation.

40.3. Preliminary technical acceptance

Preliminary technical acceptance shall be required for materials, products and components which are to be incorporated into the Works and which, due to the nature of the restoration and conservation works, require verification before installation or application.

In particular, preliminary technical acceptance shall be required for, where applicable:

- stone, brick and other masonry materials;

- mortars, plasters, renders and grouting materials;

- timber and timber products;

- roofing materials, including tiles and related components;

- paints, coatings and surface treatment materials;

- metal elements and products;

- doors, windows and other joinery;

- materials used for the repair, conservation or completion of existing historic building elements; and

- any other material or product identified in the approved restoration project or requested by the Supervisor.

The Contractor shall submit a written request for preliminary technical acceptance to the Supervisor sufficiently in advance of the planned incorporation or use of the relevant material or component. The request shall include, as applicable, the manufacturer's technical data, certificates of conformity, test reports, samples, product specifications and information concerning the origin and proposed use of the material.

No material or component requiring preliminary technical acceptance shall be incorporated into the Works before it has been accepted by the Supervisor.

The Supervisor's preliminary technical acceptance shall not relieve the Contractor of its responsibility for the conformity, quality, suitability and performance of the materials and components in accordance with Article 40.5 of the General Conditions.

Article 41	Inspection and testing

The works and the objects, appliances, equipment or materials used in their construction must comply with:

The contractor company must obtain material approval from the administration before starting the implementation of each item, confirming that the materials to be used comply with the relevant specifications. During material selection, the materials proposed by the contractor must have been manufactured in accordance with the latest version of TSE or TSEK standards and submitted to the administration for approval.

The contractor shall present the materials to the administration for approval in a timely manner so as not to disrupt the work schedule, and shall be responsible for any delays that may occur. The material selection will only be finalized upon approval by the administration. If necessary, approval records shall be kept and presented to the temporary and final acceptance commissions upon completion of the works.

All types of materials required for the works will be brought to the construction site and will be protected against adverse environmental and weather conditions.

The Contractor shall provide and install temporary lighting and electrical energy of sufficient quality for all necessary parts of the works and shall take all necessary measures to ensure the safety of all personnel related to these installations. The Contractor shall provide sufficient lighting as accepted by the administration for the proper execution and inspection of the works. If the administration does not consider this lighting sufficient, the Contractor shall make the requested additional lighting arrangements.

In case the administration requests it, the Contractor shall have the material samples tested in a laboratory or institution approved by the administration, with the costs covered by the Contractor, and shall report the results to the administration.

During the construction works, any roads, infrastructure, pavements, coatings, green areas, environmental arrangements, signs, traffic lights, etc., that are removed, damaged, or deteriorated shall be repaired and restored to their original condition.

Article 43	Ownership of plant and materials

43.2	The Contractor is obliged to take out “all risk” insurance, against risks such as natural disasters (earthquake, flood, landslide, storm, fire) as well as theft and sabotage, for all types of vehicles, materials, equipment, work and service machinery, vehicles, and facilities at the work sites, and for the works subject to the contract, depending on their characteristics and nature, covering the period from the commencement date of the works until the provisional acceptance date.

Article 44:	General principles for payments

44.1	Payments shall be made in euro.

44.2	If invoices are submitted to the contracting authority, the contractor shall inform the European Commission thereof by sending a copy to Contracting authority who will share the documents with the Programme Authority and National Authority of the programme through its regular financial reports and controls made by the controllers.

44.3	By derogation, pre-financing payment to the contractor for the lump-sum advance shall be made within 30 days. Interim payments to the contractor of the amounts due under each of the interim payment certificates approved by the supervisor shall be made within 90 days, and the final payment to the contractor of the amounts due after the final statement of account issued by the supervisor shall be made within 90 days.

Any payment may be offset against outstanding debts of any consortium member.

Article 46	Pre-financing

46.1	The only pre-financing granted to the contractor, is the lump sum advance referred to in Article 46.1(a).

46.2	By derogation to Article 46.2 of the general conditions, the lump sum advance referred to in Article 46.1(a) shall be 10% of the original contract price.

46.3(c) No pre-financing shall be granted until provision, for the full amount of the pre-financing, of a financial guarantee issued in accordance with Article 15.3 and 15.6 which shall remain effective until the pre-financing has been completely repaid by the contractor out of interim payments under the contract;

46.8	Repayment of the pre-financing shall take the form of deductions based on monthly claims.

- The flat-rate pre-financing (maximum of 10 %) shall be repaid by means of deductions from instalments and, if necessary, the balance due to the contractor. This repayment shall begin with the first instalment and be completed, at the very latest, by the time 80 % of the amount of the contract has been paid.

Repayment shall be made in the same currency as the pre-financing.

The amount to be deducted from each instalment shall be calculated using the following formula:

where:

R = the amount to be repaid

Va = the total amount of pre-financing

Vt = the initial contract amount

D = the amount of the instalment.

The result is rounded up to two decimal places.

- The pre-financing for plant, machinery and tools — and the pre-financing for other major prior outlays (20 % maximum) — shall be repaid by means of deductions from instalments and, if necessary, the balance due to the contractor. Repayment shall begin with the first instalment and end, at the very latest, by the time 90 % of the amount of the contract has been paid.

The amount to be deducted from each instalment shall be calculated using the following formula:

where:

R = the amount to be repaid

Va = the total amount of pre-financing

Vt = the initial contract amount

D = the amount of the instalment.

Article 47	Retention monies

47.1	Ten per cent (10%) of each amount certified for payment under interim payment certificates shall be retained by the Contracting Authority as retention money to guarantee the Contractor's obligations during the defects liability period.

47.2  At the Contractor's request and subject to the approval of the Contracting Authority, the retention monies may be substituted by a retention guarantee in accordance with Article 47.2 of the General Conditions. The retention guarantee shall comply with the requirements of Articles 15.3 and 15.6 and shall be submitted no later than the date fixed for the commencement of the Works.

The retention monies or the retention guarantee shall be released in accordance with Article 47.3 of the General Conditions.

This retention/guarantee shall be released:

  - After all deficiencies are corrected, or

  - After the provisional acceptance approval date if no deficiencies exist.

Article 48	Price revision

There will be no price revision.

Article 49	Measurement

Under the conditions imposed by the special conditions and general conditions, the amounts due shall be calculated through the following tranches, expressed as percentage of the contract price:

|  | Percentage | Nature | Timing |
| --- | --- | --- | --- |
| 1. | 10% | Lump-sum advance of Article 46.1(a) | After conclusion of the contract and agains pre-financing guarantee |
| 2. | 20% | Interim payment of Article 50 | After completion of 30 % of the firm quantities for which the contractor submitted its all-in price. |
| 3. | 30% | Interim payment of Article 50 | After completion of 60 % of the firm quantities for which the contractor submitted its all-in price. |
| 4. | 30% | Interim payment of Article 50 | After issuing of the certificate of provisional acceptance. |
| 5. | 10% | Retention money of Article 47 | Within 45 days of the issuing of the signed final statement of account and provisional acceptance of the works |

Payment will be done against invoice.

Invoice Requirements:

The Contractor's invoice must include the following details:

  - Contract reference number and contract title.

  - A clear description of the services provided, including the scope of work or tasks completed.

  - Total amount due, inclusive of VAT, and clearly indicating the VAT amount.

  - Bank account details of the Contractor for payment.

Approval and Issuance: The invoice may only be issued after:

  - Approval of the services provided by the Contracting Authority.

  - The signing of an acceptance protocol by both parties, confirming the satisfactory completion of the services.

Supporting Documents: The invoice must be accompanied by the following supporting documents: The signed acceptance protocol.

Article 50	Interim payments

50.1	The Contractor’s payments shall be made on a periodically progress payment basis, calculated on the base of the table in Art. 49.1 by the Contracting Authority. Invoices issued by the Contractor shall indicate progress payment amount + VAT.

Progress payment reports shall be prepared in accordance with the provisions of the national relevant legislation. These reports shall include attachments and as-built drawings showing the technical calculations for the completed works, and shall be examined by the supervisory organization. Legal deductions shall also be applied. Reports shall be prepared within the 10 days from the finalization of the relevant % from the works.

Once the progress payment reports are signed by the Contractor or their representative and submitted to the Contracting Authority, they shall be approved by the Authority within thirty (30) days, and payment shall be processed within thirty (30) days following approval.

The progress payment files submitted by the Contractor shall be inspected on-site by the technical commission appointed by the Contracting Authority before any payment is made (including any additional works requested by the Contracting Authority). The Contractor is also obliged to submit a physical progress report to the Contracting Authority together with each interim / final progress payment file.

Article 51	Final statement of account

51.(1) and (2)	The contractor shall, submit to the supervisor a draft final statement of account when it applies for the final acceptance certificate. In order to enable the supervisor to prepare the final statement of account, the draft final statement of account is submitted with supporting documents showing in detail the value of the work done in accordance with the contract and all further sums which the contractor considers to be due to it under the contract.

51.2	Within 30 days from issuing the final acceptance certificate referred to in Article 62, the supervisor shall prepare and signed the final statement of account.

Article 53	Delayed payments

53.1	By derogation from Article 53.1 of the general conditions, once the time-limit referred Article 44.3 has expired, the contractor shall be entitled to late-payment interest at the rate and for the period mentioned in the general conditions.

However, when the interest calculated in accordance with the first subparagraph is lower than or equal to EUR 200, it shall be paid to the creditor only upon a demand submitted within two months of receiving late payment.

Article 60	Provisional acceptance

60.1	In complement to Article 60.1 of the general conditions after the provisional acceptance has been carried out, the Contractor shall not be held responsible for risks that may arise due to causes not attributable to the Contractor and that may affect the construction.

However, the Contractor shall remain responsible for the structural integrity of the works from the date of provisional acceptance. The Contractor’s obligations are determined in accordance with the laws of the Republic of Türkiye.

Article 61	Defects liability

61.1	The defects liability period is defined as the period commencing on the date of provisional acceptance, during which the contractor is required to make good any defect in, or damage to, any part of the work which may appear or occur during this period as notify by the supervisor or the contracting authority. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the general conditions. The maximum duration of the defects liability period is 365 days.

Article 68	Dispute settlement

68.4	Any dispute arising out of or relating to this contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of the courts of Edirne, Türkiye in accordance with its national legislation.

Article 72	Data protection

For the purpose of Article 72 of the general conditions, for the part of the data transferred by the contracting authority to the European Commission:

- the controller for the processing of personal data carried out within the Commission is the head of legal affairs unit of DG International Partnerships.

- the privacy statement is available at

https://wikis.ec.europa.eu/display/ExactExternalWiki/Annexes.

1.	Processing of personal data related to the implementation of the contract by the contracting authority takes place in accordance with the national legislation of the state of the contracting authority and with the provisions of the respective financing agreement.

2.	To the extent that the contract covers an action financed by the European Union, the Contracting Authority may share communications related to the implementation of the contract, with the European Commission. These exchanges shall be made to the Commission, solely for the purpose of allowing the latter to exercise its rights and obligations under the applicable legislative framework and under the financing agreement with the Partner country – contracting authority. The exchanges may involve transfers of personal data (such as names, contact details, signatures and CVs) of natural persons involved in the implementation of the contract (such as contractors, personnel, experts, trainees, subcontractors, insurers, guarantors, auditors and legal counsel). In cases where the contractor is processing personal data in the context of the implementation of the contract, he/she shall accordingly inform the data subjects of the possible transmission of their data to the Commission. When personal data is transmitted to the Commission, the latter processes them in accordance with Regulation (EU) 2018/1725 of the European Parliament and of the Council of 23 October 2018 on the protection of natural persons with regard to the processing of personal data by the Union institutions, bodies, offices and agencies and on the free movement of such data, and repealing Regulation (EC) No 45/2001 and Decision No 1247/2002/EC and as detailed in the specific privacy statement published at ePRAG.

Article 73	Further additional clauses

# Environmental Requirements

# The construction works shall be carried out in such a way as to minimize any undesirable potential impacts on both the environment and the surrounding residential areas. The Contractor shall be obliged to comply with the applicable environmental regulations.

The contractor shall comply with applicable obligations in the fields of environmental, social and labour law established by Union law, national law, collective agreements or by the international social and environmental conventions listed in Annex X to Directive 2014/24/EU.

The Contractor shall be responsible for ensuring environmental safety at the construction site.

# Compliance with Laws

# Conditions relating to the employment of workers in Türkiye shall be observed, and compliance with all regulations, laws, and principles governing the employment of all categories of workers shall be mandatory.

# Occupational Health and Safety Responsibilities

# The Contractor shall be responsible for ensuring the occupational health and safety of all employees at its own expense. Within this scope, the Contractor’s responsibilities include, but are not limited to:

- Ensuring that employees benefit from services provided by an occupational safety specialist, workplace physician, and, if required, other health personnel.

- Conducting health monitoring of employees.

- Preventing occupational risks and providing appropriate training and information.

- Organizing and implementing all necessary measures, arrangements, and provision of equipment.

- Adjusting health and safety measures according to changing conditions and improving the current situation.

- Monitoring and inspecting compliance with occupational health and safety measures at the workplace, and correcting any non-compliance.

# All measures required under the occupational health and safety legislation are the responsibility of the Contractor.

# Visibility/Recognition Requirements

# Infrastructure works within projects financially co-funded by European Union through Interreg IPA Bulgaria- Türkiye Programme 2021-2027 shall be promoted with explanatory boards presenting the project and European Union’s support in line with the visualization rules of the programme.

* * *

In the event of cofinancing, the EU-contribution must normally be entered as a lump sum in euro.

OJ L 205 of 21.11.2018, p. 39.