Technical Specification for the Preparation of the Heat Resilience Strategy for Uzunköprü Municipality

1. Data Collection and Analysis Methods

1.1 Mapping of Land Use Change

Tasks:

- Analyze land use changes over the last 20 years land cover data.

- Identify factors contributing to increased heat stress through land use changes.

- Develop thematic maps illustrating historical and current land use patterns.

Expected Results:

- Comprehensive analysis of land use transformation trends.

- Identification of critical areas where land use changes have exacerbated heat stress.

Deliverables:

- Land use change analysis report.

- GIS-based maps showing land use variations over 20 years.

- Heat stress impact assessment based on land use changes.

1.2 Open and Green Space Analysis

Tasks:

- Conduct an inventory of existing open and green spaces using GIS (Geographic Information Systems).

- Assess the sustainability, and accessibility of green spaces.

- Evaluate green space distribution and its impact on urban microclimate.

Expected Results:

- A complete database of open and green spaces within the municipality.

- Identification of gaps and opportunities for improving urban greenery.

Deliverables:

- GIS database and maps of open and green spaces.

- Assessment report on green space accessibility.

- Recommendations for enhancing green infrastructure.

1.3 Satellite Imagery and Urban Heat Island (UHI) Mapping

Tasks:

- Use LANDSAT or SENTINEL satellite data to analyze surface temperature variations.

- Identify urban heat island hotspots and assess their spatial distribution.

- Develop intervention strategies based on heat map findings.

Expected Results:

- Clear identification of UHI hotspots within Uzunköprü Municipality.

- Data-driven recommendations for mitigating heat island effects.

Deliverables:

- Satellite imagery-based UHI maps.

- Analytical report on surface temperature distribution.

- Strategic intervention plan for UHI mitigation.

2. Rainwater Management and Green Infrastructure Solutions

Tasks:

- Assess permeability of urban surfaces and identify areas for improvement.

- Propose green infrastructure solutions for enhanced stormwater management.

Expected Results:

- Improved strategies for integrating water-sensitive urban design.

- Identification of suitable locations for implementing green infrastructure projects.

Deliverables:

- GIS-based maps indicating potential locations for water-sensitive design interventions.

- Guidelines for implementing green infrastructure solutions.

3. Pilot Area Selection and Conceptual Design Development

Tasks:

- Select pilot areas based on physical, ecological, and socio-economic criteria.

- Develop conceptual designs for proposed green infrastructure solutions.

- Integrate climate adaptation measures tailored to local conditions.

Expected Results:

- Identified priority areas for implementing heat resilience measures.

- Practical, site-specific solutions for urban cooling and water management.

Deliverables:

- Report on pilot area selection methodology and justification.

- Concept diagrams illustrating proposed interventions.

- Implementation guidelines for green infrastructure projects.

4. Final Strategy Development and Recommendations

Tasks:

- Synthesize findings from all analysis steps into a comprehensive heat resilience strategy.

- Develop policy recommendations and action plans for municipal implementation.

- Organize stakeholder consultations and workshops for feedback.

Expected Results:

- A well-structured Heat Resilience Strategy for Uzunköprü Municipality.

- Clear policy recommendations and implementation roadmap.

Deliverables:

- Final Heat Resilience Strategy document.

- Policy and action plan recommendations.

- Stakeholder engagement report summarizing consultations and feedback.