ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	3

2.2.	Specific objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	4

4.3.	Project management	5

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Start date & period of implementation of tasks	5

6.	REQUIREMENTS	5

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Türkiye

## Contracting authority

Uzunkopru Municipality Administration

Cumhuriyet Mah. 19 Mayıs Cad. Nr.160 Ataturk Culture Centre

22200 Uzunkopru / Edirne / Türkiye

## Country background

Global climate change is leading to several social, environmental, economic and infrastructural risks, such as increase in temperatures, pluvial flooding, droughts and ecological changes. Increased heat waves and other ecological changes brought on by rising temperatures can result in a loss of biodiversity and the extinction of several species in the basin. The health of people, agriculture, water supplies, infrastructure and natural ecosystems in the BSB could all be adversely affected by these changes.

Undoubtedly, for these common threats in the BSB it is necessary to take serious measures, and especially joint solutions leading to reduction of the urban heat island in the urban areas. A clear knowledge gap exists for local authorities that prevents them from deploying green infrastructure on a scale that enables urban landscapes to adapt to the future impacts of climate change and build more sustainable communities. Cities and towns are not investing in green infrastructure. In order to reduce heat islands and create climate-resistant green cities, local municipalities should cooperate, work on combating climate change in line with the realistic and sustainable strategies, that includes clear information and stress the importance of the green urban infrastructure on the human lives and climate change adaptation. In this cooperation project the PPs aim to respond to these needs and to make resilient Europe and BSB by sharing joint academic intelligence in the green urban sustainable planning, provide communities with accessible green infrastructure and a better environment for healthy, sustainable and resilient cities, as well as to reduce the increasing risk from heat and its consequences.

There is a certain need for increasing the capacity of local policy makers to combat climate impacts in the target regions. It is obvious that the evaluation of the climate effects, green decisions and plans that will lead to the creation of resilient cities should be included in urban planning agenda. Municipalities should be encouraged to implement measures such as adaptation measures, sustainable energy, and climate action plans to minimize heat stress and CO2 emissions. On the other hand, it is necessary to emphasize the importance of the local communities, citizens in the target regions in the fight against climate change and promoting the importance of green spaces. It is necessary for the citizens, garden workers and especially experts responsible for the maintenance of the green urban areas and landscaping to be informed about the importance of climate-resistant green spaces, the effect of their activities on them and the climate adaptation measures that we can take all together. The policy makers and the citizens from the countries in the BSB need from more awareness-raising activities with the aim to get familiar with the climate chances and the importance of the green species that actually will lead to the development of sustainable urban resilience and to a better urban future for all. The main project’s objective is: development of sustainable green climate solutions to promote adaptation to climate change and their integration into the planning work of local authorities, supported not only by the infrastructural green restoration, but also from the scientific knowledge and expertise of the landscape, urban planning and forest experts who will actually transfer the academic intelligence to the local sustainable planning and action, by development of the international LANDLAB, services to all target countries.

## Current situation in the sector

The scope of the project Green Urban Resilience, BSB00006 is covering implementation of green infrastructural and soft actions leading to the ensuring heat mitigating in the urban areas.

Türkiye has implemented various legislative measures and strategic plans to address climate change, focusing on both mitigation (reducing greenhouse gas emissions) and adaptation (adjusting to climate impacts).

Türkiye has prepared National Climate Change Mitigation and Adaptation Strategy. The 2024-2030 Climate Change Mitigation and Adaptation Strategy and Action Plans cover multiple sectors, including industry, energy, buildings, transportation, agriculture, waste, and land use. These plans include 49 strategies and 260 actions, incorporating aspects such as just transition and carbon pricing. Türkiye’s Climate Change Adaptation Strategy and Action Plan evaluates the potential effects of climate change, using regional climate projections and hazard analyses. The plan aims to enhance resilience by addressing climate risks and developing sector-specific adaptation measures.

Additionally, Türkiye’s Long-Term Climate Strategy, approved on November 4, 2024, by the Climate Change and Adaptation Coordination Board, defines a roadmap for reaching net-zero emissions by 2053.

The Uzunköprü Municipality strictly following these strategic measures of the country is implementing the project Green Urban Resilience, BSB00006. The services will be implemented in the scope of this project, which is providing opportunity for application of the best practices in green urbanization by infrastructural investments that will lead directly to the decreasing of the UHI effect in the pilot cities of Uzunkopru.

Urban green spaces are recognized as one of the most convenient and accessible ways to reduce the effects of rising temperatures in urban environments. In the “Report on the Implementation of the EU Strategy” in 2018, its stated that there is a need to create more green spaces in order to protect people from heat waves in urbanized regions and that adaptation models and region-specific scientific data production should continue with different EU initiatives. In order to make the target regions resistant to climate change and to develop their capacities, effective solutions have been provided as integrated scientific urban green methodology and awareness-raising-capacity building activities.

## In Uzunkopru a local strategic report for heat resilience will be prepared, demonstrating clearly the situation of the cities on the side of their green existing sources and the measures for prioritising green infrastructure in the cities with aim fighting with the climate change intensifies and rising temperatures.

Additionally local training activities and public awareness events will be organized.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is :

LOT 1: Organizing Measuring Activities in Uzunköprü

The overall objective of this action is to support Uzunköprü Municipality in realization of two measuring walks and measuring by air, by providing transport in Uzunköprü, catering of at least 10 people max 15 people for two days each in Uzunköprü and ensuring organization of workshop with the experts, printing of materials and questionaries for the measuring activities.

Specific Objectives

- Providing support to the municipality administration for organization two measurements of urban heat stress and thermal discomfort in the town.

- Provide transport, catering, printing of materials, workshop organization services for at least 10 people for two days * two times.

LOT 2: Organization of Local Trainings in Uzunköprü

Overall Objective The objective of this action is to be provided organizational services for realization of the trainings: two one day training events for local stakeholders and target groups in Uzunkopru, including citizens of the town: msx 30 people per event.

Specific Objectives

- Organize interactive training sessions with ensuring training area, sound and visualization system and catering for municipal staff, urban planners, and environmental professionals – one day event in Uzunköprü

- Ensuring transport and announcement of the training in the town

- Ensuring local logistic of the event and trainers – one trainer for two days.

LOT 3: Elaboration of Heat Resilience Strategy for Uzunköprü Municipality

Overall Objective To develop a comprehensive Heat Resilience Strategy that will guide Uzunköprü Municipality in mitigating the impacts of urban heat islands and increasing climate resilience.

Specific Objectives

- Assess current urban heat stress levels and vulnerability.

- Formulate strategic recommendations for green and blue infrastructure solutions.

- Provide a roadmap for policy implementation to enhance urban climate resilience.

LOT 4: Design, Translation, and Printing Services

Overall Objective To ensure effective dissemination of project materials and knowledge-sharing through high-quality design, translation, and printed materials in line with the visualization rules of the programme.

Specific Objectives

- Design project promotional materials, guides, and training materials.

- Provide professional translation services for multilingual accessibility.

- Printing and delivery services to the Contracting authority.

LOT 5: Communication Services for the Project

Overall Objective To increase awareness and stakeholder engagement through targeted communication strategies and media outreach.

Specific Objectives

- Develop and implement a project communication plan.

- Manage media relations, press releases, and social media campaigns.

- Support organizaiton of project events and engagement activities to promote project goals.

- Provide technical expertise in communication services, including content creation, public relations, and online engagement.

- Design, develop, and maintain a project website for the Green Urban Resilience Project in line with the visualizaiton rules of the programme.

- Ensure regular updates to the website with project news, event information, and resource materials.

- Ensuring communication expert engaged in the Project communication activities during the Project’s lifetime.

LOT 6: Travel and Accommodation Services

Overall Objective To facilitate travel and accommodation services for the external project participants to the partners’ locations.

Specific Objectives

- Arrange transportation and lodging for project-related events abroad and in Istanbul.

- Ensure cost-effective and efficient travel logistics.

## Expected outputs to be achieved by the contractor

The service will be paid on the basis of the delivery of the specified output(s). Payments might be totally or partially withheld if the contractual result(s) have not been reached in conformity with the detailed terms of reference. Payment(s) is/are based on the approval of this/these deliverable(s). Partial payment has to be determined according to the partial implementation of the output(s).

The expected outputs of this contract are as follows:

The expected outputs of this contract are as follows:

- LOT 1 Outputs:

  - Completion of two urban heat stress measurement walks and aerial assessments for at least 10 people for 2 days each.

  - Organization of expert workshops and provision of necessary logistical support.

- LOT 2 Outputs:

  - Organization and successful execution of two one-day training events with max 30 participants per event.

  - Provision of training area, sound and visualization materials, catering, and logistical support.

- LOT 3 Outputs:

  - Development and submission of the Heat Resilience Strategy document.

  - Completion of vulnerability assessments and policy recommendations.

- LOT 4 Outputs:

  - Design, translation, and printing of project-related materials in line with branding guidelines.

  - Delivery of printed materials to the contracting authority.

- LOT 5 Outputs:

  - Development of a communication strategy and execution of media campaigns.

  - Supporting the organizaiton of project promotion events and public outreach activities.

  - Design and continuous maintenance of the Green Urban Resilience project website.

  - Coordination the work on creation and distribution of press releases and communication materials.

  - Coordination the visualizaiton of the Project in line with the Program visibility  rules.

- LOT 6 Outputs:

  - Coordination and successful arrangement of travel and accommodation for project participants.

  - Ensuring compliance with cost-efficiency and scheduling requirements.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- LOT 1: Necessary transport vihecles, meeting areas, agenda of the measurement activities are available, and weather conditions allow for successful data collection.

- LOT 2: Local stakeholders, municipal staff, and citizens actively participate in training sessions and apply learned practices.

- LOT 3: Sufficient baseline data is available, and local authorities are committed to integrating the Heat Resilience Strategy into urban planning.

- LOT 4: Timely production of high-quality, accurately translated, and printed materials in compliance with branding and visualization rules.

- LOT 5: Effective stakeholder engagement through communication efforts, with timely updates and successful outreach via website and social media channels.

- LOT 6: Travel and accommodation services are arranged efficiently, without major logistical disruptions.

## Risks

- LOT 1: Technical or logistical issues may delay measurement activities; mitigation: having contingency plans and backup equipment. Lack of coordination with the experts and the company providing catering, trasport and other organizaiton services.

- LOT 2: Low participation rates may affect training effectiveness; mitigation: early promotion and local stakeholder engagement.

- LOT 3: Delays in data collection or analysis may impact strategy development; mitigation: ensuring collaboration with expert teams and timely coordination.

- LOT 4: Printing or translation errors could impact information dissemination; mitigation: thorough quality control and proofreading.

- LOT 5: Lack of engagement from stakeholders or technical issues with the website could hinder communication efforts; mitigation: diversifying outreach strategies and ensuring regular website maintenance.

- LOT 6: Travel disruptions, visa issues, or accommodation shortages may impact project execution; mitigation: early booking and flexibility in arrangements.

# SCOPE OF THE WORK

## General

### Description of the assignment

### The purpose of this contract is to support the Uzunköprü Municipality in implementing key activities that enhance urban climate resilience, reduce the urban heat island (UHI) effect, and increase community awareness on climate adaptation strategies. The assignment is divided into six Lots, each addressing a specific aspect of the project.

### The contractor/s will be responsible for providing services in the areas of urban heat measurement, training, strategic planning, communication, and logistics. The contract/s involves organizational, technical, and administrative tasks, ensuring that all deliverables align with the overarching objectives of the Green Urban Resilience, BSB00006 project.

### Scope of Work

### The assignment is structured around the following six Lots, with specific tasks outlined for each:

### LOT 1: Organizing Urban Heat Measurement Activities in Uzunköprü

### The contractor will organize and facilitate two urban heat stress measurement walks with at least 10 people each and upporting in logistic the works of the experts for on the ground and aerial heat assessments to evaluate thermal discomfort levels. The main tasks under this service contract include:

### Coordination of logistics for urban heat walks (identifying needed transport services, coordinating the timing, and required resources with the CA)

### Providing transportation for participants during field measurements – minibüs for at least 15 people.

### Organizing workshops with climate experts, including venue arrangements, printing materials, and facilitating discussions.

- Ensuring catering services for at least 15 people during the measurement activities in Uzunkopru – two lunches and coffee breaks – 4.

### Supporting the work of the experts in data collection and analysis work – printing survey materials for the walks, collecting list of participants, feedback forms, photos from the events.

### LOT 2: Organization of Local Training in Uzunköprü

### This lot involves organizing two one-day training events for local stakeholders, urban planners, and municipal staff and citizens to increase awareness of urban heat resilience strategies. The contractor will:

### Secure a venue with necessary facilities (seating, audiovisual equipment, and materials and possibilities for online participating).

### Arrange catering services for participants (max 30 per session).

### Engage trainers and guest speakers, ensuring their expertise aligns with the project’s objectives.

### Provide transport and logistical support to ensure smooth execution of training sessions.

### Collect participant feedback and report on the effectiveness of the sessions.

### LOT 3: Elaboration of Heat Resilience Strategy for Uzunköprü Municipality

### The contractor will develop a comprehensive Heat Resilience Strategy. The tasks include:

### Assessing urban heat stress levels and vulnerability areas in Uzunköprü.

### Identifying green and blue infrastructure solutions (e.g., increasing tree cover, urban cooling technologies).

### Developing policy recommendations for integrating climate adaptation into municipal planning.

### Engaging with key stakeholders (local government, urban planners, environmental specialists).

### Drafting a formal strategy document, which will be used as a guideline for future climate action in the region.

### LOT 4: Design, Translation, and Printing Services

### To ensure effective dissemination of project information, the contractor will:

### Design promotional and educational materials, including booklets, brochures, and posters.

### Provide professional translation services to make materials accessible in multiple languages.

### Print and deliver materials in accordance with EU branding and visibility requirements.

### Ensure high-quality formatting and visual appeal of all printed outputs.

### LOT 5: Communication Services for the Project

### This lot focuses on raising awareness and engaging stakeholders through targeted communication activities of the project. The contractor will:

### Develop and execute a communication plan, aligning with the overall project objectives.

### Manage media outreach, including press releases, interviews, and articles.

### Support the organization fo the Project promotional events, ensuring wide participation and visibility.

### Create and maintain a project website, regularly updating it with news, reports, and multimedia content, in line with the visualization guide of the Programme.

### Coordinate social media campaigns to reach a broader audience.

### Ensure all communication activities comply with EU-funded project visibility requirements.

### LOT 6: Travel and Accommodation Services

### To facilitate participation in project activities, the contractor will manage travel and accommodation logistics for external project participants / 3 people to Kavala x 3days, 3 people to Batumi x 3days, 3 people to Sozopol x3 days and 3 people to Istanbul for final event x 1 day/. The tasks include:

### Arranging transport and lodging for stakeholders/external participants traveling to project locations.

### Ensuring cost-effective bookings, prioritizing efficiency and comfort.

### Coordinating travel schedules to align with project timelines.

### Handling last-minute adjustments, including cancellations or delays.

### Ensuring accommodation of the external participants in the described target countries in at least three stars hotels and ensuring their in-town transport.

### Cross-cutting Responsibilities

### For all Lots, the contractor must ensure:

### Adherence to project timelines, ensuring timely execution of activities.

### Compliance with EU funding regulations, including financial transparency and visibility guidelines.

### Quality assurance, including proofreading, stakeholder feedback collection, and monitoring project impact.

### Collaboration with the Uzunköprü Municipality and relevant stakeholders to ensure seamless project execution.

## Geographical area to be covered

For all lots: Uzunköprü, Türkiye and only for LOT 6: Burgas (Bulgaria), Batumi (Georgia), Kavala (Greece).

## Target groups

The implementation of the Green Urban Resilience, BSB00006 project in Uzunköprü requires the active engagement of various stakeholders at the local, regional, and international levels. The project's success depends on the participation and contribution of public authorities, technical experts, community groups, and private sector representatives.

The target groups for this contract are divided into the following key categories:

Local Authorities and Decision-Makers

Primary beneficiaries:

- Uzunköprü Municipality officials and staff, particularly departments responsible for urban planning, environmental management, and climate adaptation policies.

- Regional and national governmental agencies involved in climate resilience, urban sustainability, and environmental protection.

- Policy-makers responsible for integrating green infrastructure into municipal and regional development plans.

Relevance to the project:

- This group is responsible for policy formulation, decision-making, and implementation of urban resilience strategies.

- They will use the project's findings and recommendations (e.g., the Heat Resilience Strategy) to shape future climate policies and urban planning decisions.

- They will participate in training sessions and capacity-building activities under LOT 2 to enhance their understanding of climate adaptation measures.

2. Technical Experts and Urban Planning Professionals

Primary beneficiaries:

- Climate change experts, urban planners, landscape architects, and engineers involved in designing and implementing green infrastructure solutions.

- Academics and researchers specializing in climate resilience, heat mitigation strategies, and environmental sustainability.

- GIS and remote sensing specialists engaged in urban heat measurement and analysis.

Relevance to the project:

- These experts will lead data collection efforts and support the development of the Heat Resilience Strategy (LOT 3).

- They will contribute to urban heat measurements (LOT 1) and provide technical recommendations for green and blue infrastructure solutions.

- They will train local authorities and municipal staff on best practices for climate adaptation during training sessions (LOT 2).

3. Local Communities and Citizens

Primary beneficiaries:

- Residents of Uzunköprü, including vulnerable populations (elderly, children, and those with pre-existing health conditions) who are most affected by extreme heat.

- Community groups, environmental NGOs, and local activists working on climate change adaptation and green urban initiatives.

- Business owners and private sector representatives interested in sustainable urban development and eco-friendly investments.

Relevance to the project:

- Residents will directly benefit from urban heat mitigation efforts and increased green infrastructure.

- Public awareness events (LOT 2) and project communication efforts (LOT 5) will ensure that citizens understand climate risks and the role of green infrastructure in heat resilience.

- The project will encourage active citizen participation in urban greening and community-driven climate adaptation projects.

4. Media and Communication Professionals

Primary beneficiaries:

- Local and national media outlets, journalists, and bloggers covering environmental issues and urban development.

- Social media influencers and content creators promoting climate awareness.

- Public relations and communication professionals involved in disseminating project results.

Relevance to the project:

- Media professionals will help amplify project messages through news articles, interviews, and social media coverage.

- The contractor will work closely with press and communication teams (LOT 5) to ensure effective dissemination of project outputs.

- The project website and digital campaigns will provide regular updates on key activities and achievements.

6. International and Regional Partners

Primary beneficiaries:

- Project partners in Bulgaria, Greece, and Georgia involved in urban resilience and climate adaptation initiatives.

- EU institutions, international organizations, and funding agencies supporting climate adaptation projects.

- Other municipalities in the Mediterranean and Black Sea Basin (BSB) region interested in replicating successful urban resilience strategies.

Relevance to the project:

- This group will engage in exchange visits and collaboration under LOT 6 (Travel and Accommodation Services).

- International experts will contribute to the Heat Resilience Strategy (LOT 3) by sharing best practices from their regions.

- The project will foster knowledge-sharing and networking to promote a broader regional approach to climate resilience.

## Specific work

The assignment under the Green Urban Resilience, BSB00006 project is divided into six specific Lots, each with defined tasks aimed at enhancing climate resilience, reducing the urban heat island (UHI) effect, and increasing public awareness. The contractor(s) will be responsible for delivering outputs by carrying out the following detailed tasks in a structured and timely manner:

LOT 1: Organizing Urban Heat Measurement Activities in Uzunköprü

- Logistics and Coordination of Measurement Activities:

  - Organize and facilitate two urban heat stress measurement walks with a minimum of 10 participants each to assess thermal discomfort levels.

  - Provide transport services (a minibus for at least 15 participants) during each measurement event.

  - Coordinate with climate experts and the contracting authority to finalize measurement routes and schedules.

- Workshop Organization and Data Collection Support:

  - Organize two workshops with climate experts, including securing appropriate venues, managing logistics, and facilitating expert-led discussions.

  - Ensure catering services (two lunches and four coffee breaks) for a minimum of 15 participants during measurement activities.

  - Support experts by printing and distributing survey materials for data collection during the walks.

- Documentation and Reporting:

  - Collect participant lists, feedback forms, event photos, and workshop outputs.

  - Prepare an interim report summarizing findings from the measurement activities and workshops (aligned with Section 7: Reporting Requirements).

LOT 2: Organization of Local Training in Uzunköprü

- Planning and Logistics:

  - Organize two one-day training events for local stakeholders, urban planners, municipal staff, and community members.

  - Secure venues with audiovisual equipment and facilities to support both in-person and online participation.

- Execution of Training Sessions:

  - Ensure catering services for a maximum of 30 participants per session (refreshments).

  - Provide transportation for participants when necessary.

  - Engage trainers and guest speakers with expertise in urban heat resilience and climate adaptation.

- Documentation and Evaluation:

  - distributing training materials (guides, presentations, visual aids).

  - Collect participant feedback forms and prepare a summary report for each training session.

LOT 3: Elaboration of Heat Resilience Strategy for Uzunköprü Municipality – PLEASE READ ADDITIONAL INSTRUCTIONS attached to this tender dossier.

- Assessment and Data Collection:

  - Ensuring assessment and strategy expert who will conduct a comprehensive assessment of urban heat stress levels and identify vulnerable areas within Uzunköprü.

  - Collaborate with the LandLab experts and the contracting authority to analyze data from measurement activities.

- Strategy Development by the expert:

  - Formulate strategic recommendations for green and blue infrastructure solutions (e.g., tree planting, urban cooling).

  - Prepare strategical goals to guide Uzunköprü Municipality's long-term climate resilience efforts.

- Stakeholder Engagement:

  - Organize consultation meetings with local policymakers, environmental specialists, and community representatives.

- Final Strategy Document:

  - Deliver a Heat Resilience Strategy document, including data analysis, policy recommendations, and implementation guidelines.

  - Submit an interim report summarizing the progress and a final report as outlined in Section 7.

LOT 4: Design, Translation, and Printing Services

- Design and Production of Materials:

  - Design informative and promotional materials (1-Banner, project leaflet -500, Notebooks-500, pens -500, bags - 500, Pathway Guide- 50,  Guidelines for ‘Climate Change Adaptation -10, Booklets for trainings -50) aligned with the project's visual identity.

- Translation Services:

  - Provide professional translation of project materials into necessary languages for wider dissemination.

- Printing and Delivery:

  - Ensure high-quality printing of project deliverables in compliance with EU branding and visibility guidelines.

Technical specificaitons:

- Banner - 1 item,

  Setup Dimensions: 200 cm height - 85 cm width

  Digital Print Area: 200 cm height - 85 cm width

  Print Replacement: A new print can be made and replaced for the product.

  Material: Entirely made of aluminum.

  Feature: The bottom roller system automatically retracts the visual and keeps it taut.

- project leaflet  A4- 500 copies,

  Paper: 130 gsm Glossy Coated

  Printing Type: Double-Sided Printing

  Printing Color: Full Color

  Size: A4 / 21x30 cm

- Notebooks A5 /100 sayfa/-500 copies,

  Size: 15 cm x 21 cm (A5)

  Inner Page Design: Unlined

  Number of Pages: 50 sheets (100 page)

  Paper Weight: 90 gsm

  Cover Type: Black, 350 gsm colored according to visualization design of the programme

- pens -500 item,

The ballpoint pen should have an ergonomic grip and a hard body.

- Tip Size: 1mm

- Ink Color: Black

- With the logo of the programme

- Cardboard bag – 500 items /34cm x 40cm x 14cm/

- Outer Surface Printing: 4+0 color CMYK printing

- Material: 230 gsm American Bristol cardboard

- Base Cardboard: Included

- Pathway Guide- 50 unit - /25 pages max, A5 format, colored 4+0 CMTK printing/

- Guidelines for ‘Climate Change Adaptation -10 ünits - /max 25 pages, A5 format, colored 4+0 CMTK printing/

- Booklets for trainings -50 copies, A5 format, colored 4+0 CMTK printing/, 4 types of booklets – each of them 10 pages, total number of 40 pages.

  - Deliver printed materials to the Uzunköprü Municipality according to the agreed timeline.

- Reporting:

  - Submit a report documenting materials produced and delivered.

LOT 5: Communication Services for the Project

- Ensuring communication manager who will develop and coordiante implementaiton of Communication Plan:

  - Create and implement a comprehensive communication strategy aligned with the project's objectives.

- Media and Public Relations:

  - Manage press releases, media outreach, and social media campaigns to raise awareness of project activities.

  - Organize promotional events and ensure wide participation.

- Website Management:

  - Design and maintain a project website in line with the EU Communication and Visibility Requirements.

  - Ensure the website is updated with news, reports, and project outcomes throughout the contract period.

- Documentation and Reporting:

  - Deliver an interim communication report summarizing outreach activities.

  - Ensure compliance with EU visibility requirements and submit evidence of media outputs.

LOT 6: Travel and Accommodation Services

- Travel Arrangements:

  - Arrange transport and lodging for external project participants as follows:

    - 3 participants to Kavala (Greece) for 3 days

    - 3 participants to Batumi (Georgia) for 3 days

    - 3 participants to Sozopol (Bulgaria) for 3 days

    - 3 participants to Istanbul (Türkiye) for 1 day (final event)

- Accommodation Standards:

  - Ensure participants stay in at least three-star hotels and provide in-town transportation.

- Reporting:

  - Submit a travel coordination report detailing arrangements, participant feedback, and any logistical challenges.

Cross-cutting Responsibilities (for all Lots)

- Compliance with EU Regulations:

  - Ensure adherence to EU Communication and Visibility Requirements and submit periodic evidence.

- Project Sustainability:

  - Ensure that the outputs produced (e.g., training materials, strategy documents) are designed for long-term use and can support future municipal initiatives.

- Reporting and Documentation:

  - Submit interim and final reports as specified in Section 7, ensuring comprehensive documentation of tasks and outputs.

- Quality Assurance:

  - Implement quality control measures across all deliverables, including translation accuracy, data validity, and compliance with EU standards.

## Project management

### Responsible body

The responsible body for the management of the contracts under each Lot is the Contracting authority: Uzunköprü Municipality, Türkiye.

### Management structure

The management structure of the project consists from Project Implementation Team and Steering Committee team.

The Contractor could discuss the time frame and the implementation of its tasks with the Project Manager.

### Facilities to be provided by the contracting authority and/or other parties

The Contracting authority will provide information and documentation for each event – time of implementation, expected number of participants, materials to be printed, organizational information, etc. Some of the activities, for example training activities could be implemented in the established green area – community park in Uzunkopru.

For Lot 3: Contracting authority and LandLab experts will provide some initial analyses for the current situation in the Uzunkopru achieved in the scope of the made thermal discomfort walks and measuring activities in the town.

# LOGISTICS AND TIMING

## Location

For all lots: Uzunköprü, Türkiye and only for LOT 6: Burgas (Bulgaria), Batumi (Georgia), Kavala (Greece).

## Start date & period of implementation of tasks

The intended start date is March 2025 and the period of implementation of the contract will be:

LOT 1: Organizing measuring activities in Uzunkopru: 18 months /March 2025 – September 2026/

LOT 2: Organization of local trainings in Uzunkopru: 18 months /March 2025 – September 2026/

# LOT 3: Elaboration of Heat Resilience Strategy for Uzunkopru Municipality: 18 months /March 2025- September 2026/

# LOT 4: Design, translation and printing services: 18 months /March 2025- September 2026/

# LOT 5: Communication services for the project: 18 months /March 2025- September 2026/

# LOT 6: Travel and Accommodation services: 18 months /March 2025- September 2026/

from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Personnel

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be able to provide input as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well on any potential interference or conflict of interest of the proposed expert in his/her function as expert and his/her present or previous functions working as civil servant. Moreover proof should be submitted that the expert is seconded or on personal leave.

The selection procedures used by the contractor to select the experts who provide input to the contract must be transparent, must guarantee the absence of professional conflicting interests and the absence of any discrimination based on former or current nationality, gender, place of residence, or any other ground. The findings of the selection panel must be recorded.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Experts

Only for: LOT 3 and LOT 5:

LOT 3: Elaboration of Heat Resilience Strategy for Uzunkopru Municipality

Key expert: Heat Resilience Planning expert

Education: University degree (preffered Master’s or PhD) in Climate Science, Environmental Engineering, Landscaping planning, Urban Planning, Engineering, Public Health, Sustainability, or a related field.

Professional Experience

- At least 2 years of experience in landscaping planning, urban planning, measuring activities, climate change adaptation, heat resilience planning, urban sustainability, or disaster risk reduction.

- Proven track record in developing heat resilience planning / strategies, climate adaptation plans, urban planning or urban heat mitigation projects.

- Preffered: Familiarity with EU and international climate policies, including frameworks such as the EU Adaptation Strategy and UN Sustainable Development Goals (SDGs).

Technical Skills & Knowledge

- Strong understanding of urban heat island (UHI) effects, climate risk modeling, and heat adaptation measures.

- Experience with GIS, remote sensing, or climate data analysis is an asset.

- Knowledge of nature-based solutions, urban greening, water-sensitive urban design, and heat stress mitigation strategies.

- Ability to develop policy recommendations and technical guidelines for municipalities.

Soft Skills

- Strong analytical, strategic planning, and problem-solving skills.

- Excellent communication and stakeholder engagement abilities.

- Ability to work collaboratively with diverse stakeholders, including policymakers, researchers, and local communities.

- Knowledge in English is an asset; Fluency of Turkish is required.

LOT 5: Communication services for the project

Key expert: Communication expert of the project

- A degree in communication, public relations, journalism, marketing, or a related field or at least 5 year of experience in media relations, advertisement, promotion and printing service sector and similar services.

- Proven experience in managing digital media, content development, and public outreach campaigns.

- Strong ability to develop and execute communication strategies aligned with project goals.

- Excellent writing, editorial, and presentation skills tailored to different audiences.

- Experience in content management, and social media optimization.

- Familiarity with climate resilience, sustainability, or environmental projects is an asset.

- Strong organizational and coordination skills to manage communication deliverables effectively and coordinate the communication activities with the partners.

- Fluency in English and Turkish, with strong interpersonal and cross-cultural communication skills.

The Organisation and Methodology should demonstrate how the contract will comply with these requirements to accomplish the desired output(s). The Organisation and Methodology may include the name of an expert and his profile. Compliance (yes/no answer) of the team (as a whole) with the requirements will be checked, but there will be no marks given to the experts.

### Support facilities & backstopping

The costs for support facilities, including backstopping, are included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert providing input to the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion. The contracts under each lot do not entail reimbursable / incidental expenditures to the contractor.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original:

- Interim Reports of maximum 5 pages to be produced after finalization of each task under each contract and request for payment by the contractor. In the report the contractor shall describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the inception report.

Final report of maximum 5 pages (main text, excluding annexes). This report shall be submitted no later than 10 days after finalization of all tasks under the contract, before issuing of the final request for payment. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The project’s success will be monitored using quantitative and qualitative performance indicators, ensuring a structured evaluation of outcomes. The contractor must measure and report on the following indicators:

- LOT 1:

  - Number of heat measurement walks completed (target: 2).

  - Number of participants engaged in measurements (target: at least 10 per session).

  - Data collected on urban heat stress levels and vulnerability zones.

- LOT 2:

  - Number of training sessions held (target: 2).

  - Attendance records for training sessions (target: max 30 per session).

  - Percentage of participants reporting increased knowledge on urban heat resilience strategies.

- LOT 3:

  - Completion of the Heat Resilience Strategy document.

  - Number of strategic document developed and presented to Uzunköprü Municipality /one/.

  - Level of integration of recommendations into municipal planning processes.

- LOT 4:

  - Number of materials designed, translated, and printed: 1-Banner, project leaflet -500, Notebooks-500, pens -500, bags - 500, Pathway Guide- 50,  Guidelines for ‘Climate Change Adaptation -10, Booklets for trainings -50).

  - Compliance with EU branding and visibility guidelines.

- LOT 5:

  - Number of press releases and media engagements.

  - Frequency of project website and social media updates.

  - Stakeholder engagement levels in promotional events.

- LOT 6:

  - Number of travel and accommodation arrangements successfully completed.

  - Feedback from external participants on travel and lodging arrangements.

8.2. Special Requirements

- The contractor must ensure compliance with EU-funded project reporting standards.

- Reports must include photographic evidence, participant feedback, and summary analyses.

- Indicators must be reviewed periodically, with recommendations for improvement where necessary.

* * *